## Wx
PROJECT REPORT
Group | Group 4
Week | <14/06/2021-20/06/2021>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
Doc | SRS_Screen Details | Hạnh
| SRS_Screen Flow | Hoàng
| Design | Hà
CODE | Chỉnh sửa lại phần Register, Login, các Entity, database | Hà
| Code filter và mã hóa mật khẩu | Hoàng
| Chỉnh sửa front-end (SignUn, SignUp, | Thái An
thêm home screen cho mentee)
| code view mentor profile, my profile, following request, thống nhất các đường dẫn url | Thu An
RESEARCH | Tiếp tục nghiên cứu code SpringMVC | All
| Tổng hợp tài liệu | Hạnh
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Lỗi Merge các branch khiến source code không thể build | Completed | Sửa lỗi ở local, merge tại local với nhánh mục tiêu, xác nhận source code có thể build
bình thường rồi mới push và tạo pull request để merge
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Admin Functions | 2021-03-07
| Rating Mentor Function | 26/06/2021
| Profiles Functions | 29/06/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C28: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue